## Risk Register
Risk ID | Threat Description | Affected Component | OWASP LLM Ref | NIST AI RMF Category | Likelihood | Impact | Risk Score | Risk Level | Recommended Control | Control Owner | Status
AI-001 | Direct prompt injection bypasses system prompt guardrails | LLM API | LLM01 | MANAGE | 4 | 5 | 20 | Critical | Input validation layer, output filtering, adversarial/red-team testing of prompts | Engineering | Open
AI-002 | Indirect prompt injection via retrieved/ingested documents causes the model to take unintended actions | LLM API | LLM01, LLM08 | MANAGE | 3 | 5 | 15 | High | Treat retrieved content as untrusted data (never as instructions); strip/neutralise embedded directives before adding to context | Engineering | Open
AI-003 | Model leaks system prompt or memorised training data fragments in responses | LLM API | LLM06 | MEASURE | 3 | 3 | 9 | Medium | Output monitoring with canary tokens; response filtering for system-prompt leakage | Engineering | Open
AI-004 | Token flooding / adversarial long inputs exhaust API quota and cost ceiling | LLM API | LLM04 | MANAGE | 3 | 3 | 9 | Medium | Per-session and per-account token/cost quotas; anomaly-based throttling | Engineering | Open
AI-005 | PII over-retrieval exposes other customers' data in the active context window | RAG Pipeline | LLM06 | MANAGE | 4 | 5 | 20 | Critical | Implement retrieval scoping by authenticated user/session ID; enforce row-level security in Postgres | Data Engineering | Open
AI-006 | Crafted queries retrieve data for accounts other than the authenticated user (broken retrieval scoping) | RAG Pipeline | LLM02 | MANAGE | 4 | 5 | 20 | Critical | Enforce retrieval scoping and validate query parameters against session identity server-side | Data Engineering | Open
AI-007 | Attacker-controlled content ingested into the knowledge base poisons retrieval results | RAG Pipeline | LLM03 | MEASURE | 2 | 4 | 8 | Low | Content integrity checks and provenance validation on the knowledge-base ingestion pipeline | Data Engineering | Open
AI-008 | Vector store / embedding misconfiguration allows raw document retrieval outside the RAG flow | RAG Pipeline | LLM06 | MANAGE | 2 | 4 | 8 | Low | Harden vector store access controls; restrict direct query access to the retrieval service only | Data Engineering | Open
AI-009 | JWT forgery or token replay allows session impersonation | API Gateway | OWASP API2:2023 (no direct LLM Top 10 mapping) | MANAGE | 3 | 5 | 15 | High | Short-lived JWTs, signing key rotation, replay detection (nonce/jti tracking) | Security Engineering | Open
AI-010 | No per-user rate limiting allows a single account to exhaust shared backend capacity | API Gateway | LLM04 | MANAGE | 3 | 3 | 9 | Medium | Per-user and per-IP rate limiting at the API Gateway layer | Engineering | Open
AI-011 | Insufficient authorization checks allow a customer-tier token to reach admin-only endpoints | API Gateway | OWASP API5:2023 (no direct LLM Top 10 mapping) | MANAGE | 4 | 4 | 16 | High | Enforce function-level authorization checks server-side for all admin endpoints | Engineering | Open
AI-012 | Logs store full prompts/responses containing PII in plaintext, readable by broad internal staff | Audit Logs | LLM06 | GOVERN | 4 | 4 | 16 | High | Redact/mask PII in logs before persistence; restrict log access via RBAC | Security Engineering | Open
AI-013 | Logs are not tamper-evident so actions cannot be reliably attributed after an incident | Audit Logs | OWASP A09:2021 (no direct LLM Top 10 mapping) | GOVERN | 2 | 3 | 6 | Low | Enable write-once/immutable log storage (e.g. S3 Object Lock) with cryptographic integrity checks | Security Engineering | Open
AI-014 | Log pipeline lacks immutable storage, allowing deletion or alteration of evidence post-incident | Audit Logs | OWASP A09:2021 (no direct LLM Top 10 mapping) | MANAGE | 2 | 3 | 6 | Low | Immutable/write-once log storage (same control as AI-013) | Security Engineering | Open
AI-015 | LLM-recommended actions (ticket escalation, refund initiation) are auto-executed without human confirmation (excessive agency) | Admin Panel | LLM08 | GOVERN | 4 | 5 | 20 | Critical | Require human-in-the-loop confirmation for any account-impacting action recommended by the LLM | Product / Engineering | Open
AI-016 | Admin panel authentication lacks MFA, increasing account takeover risk for high-privilege users | Admin Panel | OWASP A07:2021 (no direct LLM Top 10 mapping) | MANAGE | 3 | 4 | 12 | Medium | Enforce MFA for all admin panel accounts | IT Security | Open

## Summary
SupportBot v2 Risk Register — Summary
Risk Level | Count
Critical | 4
High | 4
Medium | 4
Low | 4
Total Risks | 16